MEETING 1

| Date of Meeting | 13/10/2025 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda (Online) |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | Self-Introductions & Team Building We were each tasked with reading a paper from the reference over the weekend. In this meeting each person summarised their paper, with the aims that together we can build a clearer picture of the project background, and with the goal that each person becomes an expert in a specific aspect of the background e.g. Simran on HCC, Yash on TME, Liu on LSECs and Miguel on Epigenetics in HCC. Miguel then introduced the workflow system on GitLab that he set up, and a projected project timeline in a Gantt chart. He also provided tasks until the next important first meeting with Dr Gendoo. Yash was assigned the organiser role and Simran was assigned the minute writer role (in place next meeting onwards) |  |  |
| Action List Literature Review (cont) Practise DEA/DAA GitLab setup Schedule Meeting | Person (s) ALL Yash, Liu ALL Yash | Task Read the other papers from the project booklet to develop a strong background understanding. Find online tutorials/guides on differential expression analysis (DEA) and differential accessibility analysis (DAA), and create a R markdown notebook in the `notebook` directory on GitLab with small sample data. Understand the basics of git. Create your own branch, pull from main etc. When Deena is back 22/10/25, send a meeting request and schedule. | Deadline 22/10/25 (meeting w/ Deena) 22/10/25 (meeting w/ Deena) 22/10/25 (meeting w/ Deena) |
| AOB (any other business) |  |  |  |
| Date of next meeting | 22/10/25 (or whenever Dr Gendoo is next available) |  |  |

MEETING 2

| Date of Meeting | 24/10/25 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda (Online) |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | - Goal: analyse ATAC-seq for HCC and combine with RNA-seq to pull integrated biological insights. - Start with the nf-core ATAC-seq pipeline as the baseline to understand the workflow. - Identify appropriate Bioconductor packages to process and analyse ATAC-seq / downstream results. - For the next meeting each person should report top 2–3 strengths and weaknesses of the Bioconductor packages they evaluated. - Create a list of immune markers relevant to our project (to be used in downstream interpretation). - Homework includes comparing ATAC-seq vs ChIP-seq. - Read the “tip of the iceberg” paper first (it’s the priority paper to understand context&methods). - Understand the tools/processes mentioned in the meeting (noted as “group on” and “barBEAR”). - Search for additional ATAC-seq datasets for HCC on GEO / Omnibus to expand sample availability. - If Saad’s data is not received by Wednesday, remind Deena and shift focus to EHMT2 regulator as the immediate target for analysis. - Once Saad’s data arrives: - Analyse the ATAC-seq data (use nf-core / chosen pipelines). - Deena will provide video links to help with the ATAC analysis. - After ATAC analysis, run the RNA-seq analysis and then integrate results (pull information from both ATAC and RNA analyses). - Next meeting with Deena is 5th November. |  |  |
| Action List | Person (s) Leo & Yash Simran & Miguel | Task - Check GEO/Omnibus for additional HCC ATAC-seq datasets and list candidate accession IDs. - nf-core ATAC-seq pipeline: inputs, outputs, workflow. - Bioconductor (or alternative) packages for ATAC/RNA analysis; prepare 2–3 strengths & weaknesses for the shortlisted ones. - Study Tip of the Iceberg paper - Immune markers relevant to HCC | Deadline 05/11/25 (meeting w/ Deena) 05/11/25 (meeting w/ Deena) 05/11/25 (meeting w/ Deena) 05/11/25 (meeting w/ Deena) 05/11/25 (meeting w/ Deena) |
| AOB (any other business) |  |  |  |
| Date of next meeting | 05/11/25 with Deena |  |  |

MEETING 3

| Date of Meeting | 23/10/25 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda (Online) |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | - Quick progress check before the meeting with Deena (5 November) - Each member briefly shared progress and current status on assigned tasks - The meeting was kept mainly to realign tasks and ensure everyone knew what to do once the data arrived. |  |  |
| Action List | Person (s) Miguel Leo & Yash Simran | Task Email Deena for data and bear access Go over the nf-core/atacseq pipeline and attempt to implement with our data. Scout for HCC / immune markers in LSECs | Deadline ASAP 05/11/25 (meeting w/ Deena) 05/11/25 (meeting w/ Deena) |
| AOB (any other business) |  |  |  |
| Date of next meeting | 05/11/25 with Deena |  |  |

| Date of Meeting | 03/11/25 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda (Task Allocation via WhatsApp) |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | No formal or informal meeting was held. However, project work resumed because the dataset from Saad finally became accessible. The team leader (Miguel) issued task assignments via WhatsApp to ensure progress before the next group meeting. |  |  |
| Action List | Person (s) Yash Leo Simran | Task - Perform Differential Expression Analysis (DEA). - Generate a list of DEGs comparing EHMT2 normal vs EHMT2 knockdown samples. - Tools left to personal preference. - Perform Differential Accessibility Analysis (DAA). - Identify genomic regions with altered accessibility between EHMT2 normal vs knockdown. - Free to use chosen pipelines/tools. - Review Paper 4: Epigenetics in HCC (or other literature) to compile: - HCC-related markers/genes - Immune-related markers relevant to HCC - These markers will later be cross-referenced with DEA + DAA results to evaluate whether EHMT2 knockdown influences disease-related pathways. | Deadline 06/11/25 (meeting w/ Deena) 06/11/25 (meeting w/ Deena) 06/11/25 (meeting w/ Deena) |
| AOB (any other business) |  |  |  |
| Date of next meeting | 06/11/25 with Deena (date changed) |  |  |

| Date of Meeting | 06/11/25 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda (Task Allocation via WhatsApp) |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | Access Issues: - All members reported that the BlueBear viewer wasn’t accessible. - Deena acknowledged the problem and said she would look into fixing BlueBear accessibility for everyone. By communicating with the IT. GitHub Setup: - Deena asked everyone to create GitHub accounts. - She added all members to her GitHub repository. |  |  |
| Action List | Person (s) Yash Leo Simran & Miguel | Task - Perform Differential Expression Analysis (DEA). - Generate a list of DEGs comparing EHMT2 normal vs EHMT2 knockdown samples. - Tools left to personal preference. - Perform Differential Accessibility Analysis (DAA). - Identify genomic regions with altered accessibility between EHMT2 normal vs knockdown. - Free to use chosen pipelines/tools. Literature mining, identifying additional biomarkers, and contributing to downstream interpretation. | Deadline ASAP ASAP ASAP |
| AOB (any other business) |  |  |  |
| Date of next meeting | Date TBD; (NEXT MEETING: 28/11/25- 2PM) |  |  |

| Date of Meeting | 28/11/25 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda (Task Allocation via WhatsApp) |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | In the 28 November meeting, we reviewed overall progress after BlueBear was finally fixed and everyone was able to resume their analysis work. Each member gave a brief update on what they had completed so far and where they were still facing difficulties. We also discussed the next steps for moving the project forward, including refining our individual components and improving coordination. The group agreed that we should now focus on understanding each other’s analyses especially the sequencing workflows, to ensure consistency in interpretation. We were also instructed to begin preparing our individual video presentations, since the final stage of the project is approaching. |  |  |
| Action List | Person (s) Yash & Liu Simran ALL | Task - Fix batch issues in the data. - Extract FPKM values with Yash using Salmon/Lima. - Run DESeq with batch-corrected matrix. - Refine and expand the gene-of-interest list using more literature and add references. - Check single-cell RNA-seq datasets (GEO/Omnibus) related to EHMT2. - Email Seyi to confirm video format and update the group. Prepare 5-minute voiceover PPT by 12 Dec. | Deadline 12/12/25 (meeting w/ Deena) 12/12/25 (meeting w/ Deena) 12/12/25 (meeting w/ Deena) |
| AOB (any other business) |  |  |  |
| Date of next meeting | 12/12/25 |  |  |

| Date of Meeting | 05/12/25 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | On 5 December, we met to share brief updates on our current progress as we prepared for an upcoming meeting with our supervisor, Deena. Each member outlined what they are currently working on and any ongoing tasks. We also discussed the requirement to create a 5-minute video presentation, which will serve as a project outline to be submitted in January. |  |  |
| Action List | Person (s) Yash & Liu Simran ALL | Task - Progress on batch correction; initial issues identified and partially resolved. - Continue working on FPKM extraction using Salmon/Lima. - Prepare to run DESeq on the corrected matrix; pending final validation of input data. - Refine the gene-of-interest list with additional literature references. - Explore relevant single-cell RNA-seq datasets (GEO/Omnibus) related to EHMT2. Prepare 5-minute voiceover PPT by 12 Dec. | Deadline 12/12/25 (meeting w/ Deena) 12/12/25 (meeting w/ Deena) 12/12/25 (meeting w/ Deena) |
| AOB (any other business) |  |  |  |
| Date of next meeting | 12/12/25 |  |  |

| Date of Meeting | 12/12/25 |  |  |
| --- | --- | --- | --- |
| People Attending | Yash Dhiman, Zhaoshuo Liu |  |  |
| Apologies for absence | Miguel Alburo, Simran Panda |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | On 12 December, only Yash and Liu attended the meeting and provided progress updates. They continued working on batch effect correction through data harmonization and reported a reduction in the number of outliers, indicating improvement in data consistency. Further refinement of the harmonization process is ongoing. The next meeting was scheduled for 5th February with module leads. |  |  |
| Action List | Person (s) Yash Liu Simran Miguel | Task - Continue refining data harmonization to further reduce batch effects. - Validate corrected dataset for downstream analysis readiness - Support harmonization process and monitor outlier trends. - Assist in preparing batch-corrected data for DESeq analysis. - Continue literature review and expansion of gene-of-interest list. - Progress exploration of relevant single-cell RNA-seq datasets. - Prepare to lead the next meeting on 5th February. - Coordinate team progress and ensure alignment across components. | Deadline ASAP ASAP ASAP ASAP |
| AOB (any other business) |  |  |  |
| Date of next meeting | 05/02/26 |  |  |

| Date of Meeting | 05/02/26 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | In the meeting with the module lead, the team presented their current progress on the group report. The allocated sections i.e. Introduction, Methods/Results, and Results & Discussion, were outlined, along with the plan to complete a full draft (max 2500 words) ahead of the end-of-month meeting with Deena. Feedback focused on maintaining clarity, adhering to word limits, and ensuring alignment between sections. The team will continue developing their respective sections toward the 20th February deadline. |  |  |
| Action List | Person (s) Yash Liu Miguel Simran | Task - Draft Results & Discussion (max 1000 words). - Ensure interpretation aligns with processed data and analysis outputs. - Contribute to Methods/Results section (max 500 words). - Align methods description with actual analysis performed. - Co-develop Methods/Results section. - Oversee integration of all sections into a cohesive draft. - Coordinate progress ahead of the deadline. - Draft the Introduction (max 750 words). - Ensure clear background, rationale, and linkage to project aims. | Deadline 20/02/26 20/02/26 20/02/26 20/02/26 |
| AOB (any other business) |  |  |  |
| Date of next meeting | 24/02/26 |  |  |

| Date of Meeting | 24/02/26 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | In the meeting with our supervisor Deena, the team provided a progress update on the group report, with each member working on their assigned sections. The discussion focused on current writing progress and alignment across sections. Deena advised that any additional relevant analyses should be considered and recommended keeping some word count in reserve to accommodate further results if needed. |  |  |
| Action List | Person (s) Yash Liu Miguel Simran | Task - Continue writing and refining the Results & Discussion section. - Align interpretation with current and any additional analyses. - Continue developing the Methods/Results section. - Ensure clarity and alignment with actual analyses performed. - Contributing to Methods/Results. - Oversee integration and coherence of all report sections. - Monitor overall progress and word count allocation. - Compile and format the reference list for the report. - Ensure all citations are consistent with the chosen referencing style. | Deadline 09/03/26 09/03/26 09/03/26 09/03/26 |
| AOB (any other business) |  |  |  |
| Date of next meeting | 09/03/26 |  |  |

| Date of Meeting | 09/03/26 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu, Simran Panda |  |  |
| Apologies for absence |  |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | In the meeting, the team reviewed current progress on the report and remaining analysis requirements ahead of upcoming deadlines. Miguel highlighted that additional analysis is still pending and requested submission of remaining report sections, particularly from Yash. The group aligned on finalising individual contributions and preparing material for consolidation into the full report. The meeting also confirmed coordination for continued progress ahead of the next scheduled meeting. |  |  |
| Action List | Person (s) Yash Liu Miguel Simran | Task - Email Results and Discussion draft. - Complete remaining analysis and integrate findings into written section. - Share results via WhatsApp, including upregulated/downregulated genes and open/closed genes. - Ensure clarity and consistency of reported gene sets. - Stitch together full report from all sections. - Ensure coherence, structure, and formatting consistency. - Track completion of pending inputs from team members. - Email updated Introduction section including references. - Ensure citations are complete and properly formatted. | Deadline ASAP ASAP ASAP ASAP |
| AOB (any other business) |  |  |  |
| Date of next meeting | 24/03/26 |  |  |

| Date of Meeting | 24/03/26 |  |  |
| --- | --- | --- | --- |
| People Attending | Simran Panda |  |  |
| Apologies for absence | Miguel Alburo, Yash Dhiman, Zhaoshuo Liu |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | An in-person meeting was held on 24th March with the module leads, Peter and Seyi. Simran provided an update on behalf of the team, reporting that the group had already initiated the project and was midway through drafting the report. The leads were informed about the current progress and individual contributions so far. No additional concerns or issues were raised during the discussion, and the overall progress was deemed satisfactory at this stage. |  |  |
| Action List | Person (s) All | Task - Continue writing assigned sections of the report and refine existing content. - Maintain consistency across all parts of the report in terms of structure and formatting. - Ensure all group contributions are integrated into the shared document. - Progress towards completing the first full draft of the report. - Prepare for internal review and identify any gaps in content or analysis. | Deadline ASAP |
| AOB (any other business) |  |  |  |
| Date of next meeting | 30/03/26 |  |  |

| Date of Meeting | 30/03/26 |  |  |
| --- | --- | --- | --- |
| People Attending | Miguel Alburo, Zhaoshuo Liu |  |  |
| Apologies for absence | Simran Panda, Yash Dhiman |  |  |
| Minutes A summary of the content of the meeting including an update from each group member on progress against objectives since last meeting. | A meeting was held on 30th March where the presented group members presented their findings through slides and verbal explanations. Each member discussed their respective analyses and results, highlighting the overall progress of the project. The group reported that the report writing phase is nearing completion, with plans to submit the first draft to the supervisor shortly. This will allow for feedback to be incorporated before finalising the document. The meeting concluded with agreement on progressing towards finalisation and revision based on supervisor input. |  |  |
| Action List | Person (s) All | Task - Complete final sections of the report and ensure all analysis is fully documented. - Integrate individual contributions into a cohesive first draft. - Prepare and submit the first draft of the report to the supervisor. - Await supervisor feedback and note required revisions or improvements. - Revise the report based on feedback and move towards final submission. | Deadline ASAP |
| AOB (any other business) |  |  |  |
| Date of next meeting | Not yet decided |  |  |